Upper Mainstem Eel River | SONCC-UMER.27.4.45.1 | Monitor | Track threat | Describe road threat | Describe the status and trends of road treatments and road density at least once every five years | Population wide | 3d
Upper Mainstem Eel River | SONCC-UMER.27.4.46.1 | Monitor | Track threat | Describe threat of high intensity fire | Describe trends in occurrence of high severity fire at least once every five years | Population wide | 3d
Upper Mainstem Eel River | SONCC-UMER.27.4.47.1 | Monitor | Track threat | Describe threat of invasive species | Describe status and trend of abundance and distribution of invasive species annually | Population wide | 3d
Upper Mainstem Eel River | SONCC-UMER.3.1.1.1 | Hydrology | Improve flow timing or volume | Manage flow | Conduct assessments to identify areas of improvement for water management and diversions | Cape Horn and Scott Dams | 2c
Upper Mainstem Eel River | SONCC-UMER.3.1.1.2 | Hydrology | Improve flow timing or volume | Manage flow | Make improvements to water management and diversions, based on the assessment | Cape Horn and Scott Dams | 2c
Upper Mainstem Eel River | SONCC-UMER.3.1.3.1 | Hydrology | Improve flow timing or volume | Improve regulatory mechanisms | Ensure water diversions are within their water rights | Mainstem and tributaries downstream of Scott Dam | 2b
Upper Mainstem Eel River | SONCC-UMER.3.1.34.1 | Hydrology | Improve flow timing or volume | Increase instream flows | Identify diversions in tributaries that have subsurface or low flow barrier conditions during the summer | All streams where coho salmon would benefit immediately | 2b
Upper Mainstem Eel River | SONCC-UMER.3.1.34.2 | Hydrology | Improve flow timing or volume | Increase instream flows | Increase flows during low flow periods, as described in the program | All streams where coho salmon would benefit immediately | 2b
Upper Mainstem Eel River | SONCC-UMER.3.1.35.1 | Hydrology | Improve flow timing or volume | Measure flow | Maintain flow gage annually | Upstream of Lake Pillsbury | 3d
Upper Mainstem Eel River | SONCC-UMER.3.1.39.1 | Hydrology | Improve flow timing or volume | Determine effects of marijuana cultivation | Assess cumulative effects (e.g., flow, water quality) of marijuana cultivation | Population wide | 2b
Upper Mainstem Eel River | SONCC-UMER.3.1.39.2 | Hydrology | Improve flow timing or volume | Determine effects of marijuana cultivation | If needed, develop plan to reduce effects of marijuana cultivation | Population wide | 2b
Upper Mainstem Eel River | SONCC-UMER.3.1.39.3 | Hydrology | Improve flow timing or volume | Determine effects of marijuana cultivation | Implement plan | Population wide | 2b
Upper Mainstem Eel River | SONCC-UMER.3.1.4.1 | Hydrology | Improve flow timing or volume | Educate stakeholders | Complete comprehensive flow study activities, and use them to educate water managers on how to reduce impacts to coho salmon | Population wide | 2b
Upper Mainstem Eel River | SONCC-UMER.3.1.5.1 | Hydrology | Improve flow timing or volume | Educate stakeholders | Provide incentives to landowners to reduce water consumption | Population wide | 2b
Upper Mainstem Eel River | SONCC-UMER.3.1.6.1 | Hydrology | Improve flow timing or volume | Educate stakeholders | Provide education and training on water diversion practices and facilitate compliance with pertinent laws and regulations (e.g., FGC §1600 et seq., CFPR 14 CCR 916.9, California water rights law) | Population wide | 2b
Upper Mainstem Eel River | SONCC-UMER.5.1.2.1 | Passage | Improve access | Assess fish passage | Assess benefits of passage above Scott Dam for coho salmon | Scott Dam | 3b
Upper Mainstem Eel River | SONCC-UMER.5.1.2.2 | Passage | Improve access | Assess fish passage | If passage is determined to be beneficial, develop plan to provide passage | Scott Dam | 3b
Upper Mainstem Eel River | SONCC-UMER.5.1.2.3 | Passage | Improve access | Assess fish passage | Implement plan to provide passage | Scott Dam | 3b
Upper Mainstem Eel River | SONCC-UMER.5.2.59.1 | Passage | Decrease mortality | Screen all diversions | Assess diversions and develop a screening program | Population wide | 2c
Upper Mainstem Eel River | SONCC-UMER.5.2.59.2 | Passage | Decrease mortality | Screen all diversions | Screen all diversions | Population wide | 2c
Upper Mainstem Eel River | SONCC-UMER.5.2.7.1 | Passage | Decrease mortality | Screen all diversions | Assess diversions and develop a screening program | All streams where coho salmon would benefit immediately | 2b
Upper Mainstem Eel River | SONCC-UMER.5.2.7.2 | Passage | Decrease mortality | Screen all diversions | Screen all diversions | All streams where coho salmon would benefit immediately | 2b
Upper Mainstem Eel River | SONCC-UMER.7.1.11.1 | Riparian | Improve wood recruitment, bank stability, shading, and food subsidies | Increase conifer riparian vegetation | Develop an appropriate timber harvest management plan for benefits to coho salmon habitat | Population wide (downstream of Scott Dam) | 3b
Upper Mainstem Eel River | SONCC-UMER.7.1.11.2 | Riparian | Improve wood recruitment, bank stability, shading, and food subsidies | Increase conifer riparian vegetation | Thin, or release conifers, guided by the plan | Population wide (downstream of Scott Dam) | 3b
Upper Mainstem Eel River | SONCC-UMER.7.1.11.3 | Riparian | Improve wood recruitment, bank stability, shading, and food subsidies | Increase conifer riparian vegetation | Plant conifers, guided by the plan | Population wide (downstream of Scott Dam) | 3b
Upper Mainstem Eel River | SONCC-UMER.7.1.12.1 | Riparian | Improve wood recruitment, bank stability, shading, and food subsidies | Improve timber harvest practices | Amend California Forest Practice Rules to include regulations which describe the specific analysis, protective measures, and procedure required by timber owners and CalFire to demonstrate timber operations described in timber harvest plans meet the requir | Population wide | 3d
Upper Mainstem Eel River | SONCC-UMER.7.1.13.1 | Riparian | Improve wood recruitment, bank stability, shading, and food subsidies | Reduce fire hazard | Identify forested stands for fire hazard reduction | Upland areas adjacent to streams | 3d
Upper Mainstem Eel River | SONCC-UMER.7.1.13.2 | Riparian | Improve wood recruitment, bank stability, shading, and food subsidies | Reduce fire hazard | Apply appropriate management techniques (e.g. thinning, burning) to reduce risks of high severity fire | Upland areas adjacent to streams | 3d
Upper Mainstem Eel River | SONCC-UMER.8.1.14.1 | Sediment | Reduce delivery of sediment to streams | Reduce road-stream hydrologic connection | Assess and prioritize road-stream connection, and identify appropriate treatments | All areas where coho salmon would benefit immediately (downstream of Scott Dam) | 2b
Upper Mainstem Eel River | SONCC-UMER.8.1.14.2 | Sediment | Reduce delivery of sediment to streams | Reduce road-stream hydrologic connection | Decommission roads, guided by assessment | All areas where coho salmon would benefit immediately (downstream of Scott Dam) | 2b
Upper Mainstem Eel River | SONCC-UMER.8.1.14.3 | Sediment | Reduce delivery of sediment to streams | Reduce road-stream hydrologic connection | Upgrade roads, guided by assessment | All areas where coho salmon would benefit immediately (downstream of Scott Dam) | 2b
Upper Mainstem Eel River | SONCC-UMER.8.1.14.4 | Sediment | Reduce delivery of sediment to streams | Reduce road-stream hydrologic connection | Maintain roads, guided by assessment | All areas where coho salmon would benefit immediately (downstream of Scott Dam) | 2b
Upper Trinity River | SONCC-UTR.1.2.41.1 | Estuary | Improve estuarine habitat | Improve estuary condition | Implement recovery actions for Lower Klamath River population that address the target "Estuary", including the creation/restoration of off-channel rearing habitat throughout the lower Klamath River | Klamath River Estuary | 2c
Upper Trinity River | SONCC-UTR.10.1.13.1 | Water Quality | Reduce water temperature, increase dissolved oxygen | Reduce warm water inputs | Study and evaluate methods to reduce thermal heating in Lewiston Reservoir | Lewiston Dam on mainstem Trinity | 3c
Upper Trinity River | SONCC-UTR.10.1.13.2 | Water Quality | Reduce water temperature, increase dissolved oxygen | Reduce warm water inputs | Implement plan to reduce thermal heating based on findings | Lewiston Dam on mainstem Trinity | 3c
Upper Trinity River | SONCC-UTR.10.1.14.1 | Water Quality | Reduce water temperature, increase dissolved oxygen | Increase flow | Develop a plan to address water quality and quantity | Weaver, Reading, Grass Valley, and Indian creeks, and all streams where coho salmon would benefit immediately | 2c
Upper Trinity River | SONCC-UTR.10.1.14.2 | Water Quality | Reduce water temperature, increase dissolved oxygen | Increase flow | Implement plan to address water quality and quantity | Weaver, Reading, Grass Valley, and Indian creeks, and all streams where coho salmon would benefit immediately | 2c
Upper Trinity River | SONCC-UTR.10.1.60.1 | Water Quality | Reduce water temperature, increase dissolved oxygen | Increase flow | Develop a plan to address water quality and quantity | Population wide | 2d
Upper Trinity River | SONCC-UTR.10.1.60.2 | Water Quality | Reduce water temperature, increase dissolved oxygen | Increase flow | Implement plan to address water quality and quantity | Population wide | 2d
Upper Trinity River | SONCC-UTR.10.7.57.1 | Water Quality | Restore nutrients | Add marine-derived nutrients to streams | Develop a plan to supply appropriate amounts of marine-derived nutrients to streams (e.g. carcass placement, pellet dispersal) | All streams where coho salmon would benefit immediately | 3c
Upper Trinity River | SONCC-UTR.10.7.57.2 | Water Quality | Restore nutrients | Add marine-derived nutrients to streams | Supply marine-derived nutrients to streams guided by the plan | All streams where coho salmon would benefit immediately | 3c
Upper Trinity River | SONCC-UTR.10.7.61.1 | Water Quality | Restore nutrients | Add marine-derived nutrients to streams | Develop a plan to supply appropriate amounts of marine-derived nutrients to streams (e.g. carcass placement, pellet dispersal) | Population wide | 3d
Upper Trinity River | SONCC-UTR.10.7.61.2 | Water Quality | Restore nutrients | Add marine-derived nutrients to streams | Supply marine-derived nutrients to streams guided by the plan | Population wide | 3d
Upper Trinity River | SONCC-UTR.14.2.22.1 | Invasive, Non-native Species | Reduce predation and competition | Reduce abundance of brown trout | Adopt fishing regulations and educational programs that encourage and allow for the take of an unlimited number of brown trout | Population wide | 2c
Upper Trinity River | SONCC-UTR.14.2.22.2 | Invasive, Non-native Species | Reduce predation and competition | Reduce abundance of brown trout | Euthanize all brown trout captured at CDFW weirs | Population wide | 2c
Upper Trinity River | SONCC-UTR.16.1.23.1 | Fishing/Collecting | Manage fisheries consistent with recovery of SONCC coho salmon | Incorporate SONCC coho salmon VSP delisting criteria when formulating salmonid fishery management plans affecting SONCC coho salmon | Determine impacts of fisheries management on SONCC coho salmon in terms of VSP parameters | SONCC recovery domain plus ocean; from shore to 200 miles off coasts of California and Oregon | 3d
Upper Trinity River | SONCC-UTR.16.1.23.2 | Fishing/Collecting | Manage fisheries consistent with recovery of SONCC coho salmon | Incorporate SONCC coho salmon VSP delisting criteria when formulating salmonid fishery management plans affecting SONCC coho salmon | Identify level of fishing impacts that does not limit attainment of population-specific viability criteria | SONCC recovery domain plus ocean; from shore to 200 miles off coasts of California and Oregon | 3d
Upper Trinity River | SONCC-UTR.16.1.24.1 | Fishing/Collecting | Manage fisheries consistent with recovery of SONCC coho salmon | Reduce fishing impacts to levels that do not limit recovery | Determine actual fishing impacts | SONCC recovery domain plus ocean; from shore to 200 miles off coasts of California and Oregon | 3d
Upper Trinity River | SONCC-UTR.16.1.24.2 | Fishing/Collecting | Manage fisheries consistent with recovery of SONCC coho salmon | Reduce fishing impacts to levels that do not limit recovery | If actual fishing impacts limit attainment of population-specific viability criteria, modify management so that fishing does not limit attainment of population-specific viability criteria | SONCC recovery domain plus ocean; from shore to 200 miles off coasts of California and Oregon | 3d
Upper Trinity River | SONCC-UTR.16.1.55.1 | Fishing/Collecting | Manage fisheries consistent with recovery of SONCC coho salmon | Incorporate SONCC coho salmon VSP delisting criteria when formulating salmonid fishery management plans affecting SONCC coho salmon | Determine impacts of fisheries management on SONCC coho salmon in terms of VSP parameters | Tribal lands | 3d
Upper Trinity River | SONCC-UTR.16.1.55.2 | Fishing/Collecting | Manage fisheries consistent with recovery of SONCC coho salmon | Incorporate SONCC coho salmon VSP delisting criteria when formulating salmonid fishery management plans affecting SONCC coho salmon | Identify level of fishing impacts that does not limit attainment of population-specific viability criteria | Tribal lands | 3d
Upper Trinity River | SONCC-UTR.16.1.56.1 | Fishing/Collecting | Manage fisheries consistent with recovery of SONCC coho salmon | Reduce fishing impacts to levels that do not limit recovery | Determine actual fishing impacts | Tribal lands | 3d
Upper Trinity River | SONCC-UTR.16.1.56.2 | Fishing/Collecting | Manage fisheries consistent with recovery of SONCC coho salmon | Reduce fishing impacts to levels that do not limit recovery | If actual fishing impacts limit attainment of population-specific viability criteria, modify management so that fishing does not limit attainment of population-specific viability criteria | Tribal lands | 3d
Upper Trinity River | SONCC-UTR.16.2.25.1 | Fishing/Collecting | Manage scientific collection consistent with recovery of SONCC coho salmon | Incorporate SONCC coho salmon VSP delisting criteria when formulating scientific collection authorizations affecting SONCC coho salmon | Determine impacts of scientific collection on SONCC coho salmon in terms of VSP parameters | SONCC recovery domain plus ocean; from shore to 200 miles off coasts of California and Oregon | 3d
Upper Trinity River | SONCC-UTR.16.2.25.2 | Fishing/Collecting | Manage scientific collection consistent with recovery of SONCC coho salmon | Incorporate SONCC coho salmon VSP delisting criteria when formulating scientific collection authorizations affecting SONCC coho salmon | Identify level of scientific collection impact that does not limit attainment of population-specific viability criteria | SONCC recovery domain plus ocean; from shore to 200 miles off coasts of California and Oregon | 3d
Upper Trinity River | SONCC-UTR.16.2.26.1 | Fishing/Collecting | Manage scientific collection consistent with recovery of SONCC coho salmon | Reduce impacts of scientific collection to levels that do not limit recovery | Determine actual impacts of scientific collection | SONCC recovery domain plus ocean; from shore to 200 miles off coasts of California and Oregon | 3d
Upper Trinity River | SONCC-UTR.16.2.26.2 | Fishing/Collecting | Manage scientific collection consistent with recovery of SONCC coho salmon | Reduce impacts of scientific collection to levels that do not limit recovery | If actual scientific collection impacts limit attainment of population-specific viability criteria, modify collection so that impacts do not limit attainment of population-specific viability criteria | SONCC recovery domain plus ocean; from shore to 200 miles off coasts of California and Oregon | 3d
Upper Trinity River | SONCC-UTR.17.2.1.1 | Hatcheries | Reduce adverse hatchery impacts | Identify and reduce impacts of hatchery on SONCC coho salmon | Develop and implement a Hatchery and Genetic Management Plan | Trinity River Hatchery | 2c
Upper Trinity River | SONCC-UTR.17.2.1.2 | Hatcheries | Reduce adverse hatchery impacts | Identify and reduce impacts of hatchery on SONCC coho salmon | Increase proportion of natural influence by reducing production of coho salmon smolts, adopt naturally-produced (unmarked) broodstock targets, trap and cull excess hatchery broodstock, and encourage a terminal recreational fishery to help decrease the num | Trinity River Hatchery | 2c
Upper Trinity River | SONCC-UTR.17.2.1.3 | Hatcheries | Reduce adverse hatchery impacts | Identify and reduce impacts of hatchery on SONCC coho salmon | Monitor genetic diversity by collecting tissue samples from all fish returning to the hatchery | Trinity River Hatchery | 2c
Upper Trinity River | SONCC-UTR.17.2.1.4 | Hatcheries | Reduce adverse hatchery impacts | Identify and reduce impacts of hatchery on SONCC coho salmon | Reduce genetic impacts of hatchery on wild fish by adopting a 1:1 mating protocol | Trinity River Hatchery | 2c
Upper Trinity River | SONCC-UTR.17.2.1.5 | Hatcheries | Reduce adverse hatchery impacts | Identify and reduce impacts of hatchery on SONCC coho salmon | Reduce steelhead ecological interactions by reducing hatchery steelhead production | Trinity River Hatchery | 2c
Upper Trinity River | SONCC-UTR.17.2.1.6 | Hatcheries | Reduce adverse hatchery impacts | Identify and reduce impacts of hatchery on SONCC coho salmon | Provide geographic segregation of spawning to runs of Chinook salmon, coho salmon, and steelhead by operating weirs or other systems aimed at limiting redd superimposition | Trinity River Hatchery | 2c
Upper Trinity River | SONCC-UTR.2.1.62.1 | Floodplain and Channel Structure | Increase channel complexity | Increase LWD, boulders, or other instream structure | Assess habitat to determine beneficial location and amount of instream structure needed | Population wide | 2d
Upper Trinity River | SONCC-UTR.2.1.62.2 | Floodplain and Channel Structure | Increase channel complexity | Increase LWD, boulders, or other instream structure | Place instream structures, guided by assessment results | Population wide | 2d
Upper Trinity River | SONCC-UTR.2.1.9.1 | Floodplain and Channel Structure | Increase channel complexity | Increase LWD, boulders, or other instream structure | Assess habitat to determine beneficial location and amount of instream structure needed | Mainstem above Douglas City, Grass Valley, Indian, Hayfork, Reading, Weaver, East Fork Weaver Creek, and all streams where coho salmon would benefit immediately | 2c
Upper Trinity River | SONCC-UTR.2.1.9.2 | Floodplain and Channel Structure | Increase channel complexity | Increase LWD, boulders, or other instream structure | Place instream structures, guided by assessment results | Mainstem above Douglas City, Grass Valley, Indian, Hayfork, Reading, Weaver, East Fork Weaver Creek, and all streams where coho salmon would benefit immediately | 2c
Upper Trinity River | SONCC-UTR.2.2.43.1 | Floodplain and Channel Structure | Reconnect the channel to the floodplain | Improve regulatory mechanisms | Improve protective regulations for beaver and develop guidelines for relocation that are practical for restoration groups | Population wide | 3d
Upper Trinity River | SONCC-UTR.2.2.63.1 | Floodplain and Channel Structure | Reconnect the channel to the floodplain | Construct off channel habitats, alcoves, backwater habitat, and old stream oxbows | Identify potential sites to create refugia habitats. Prioritize sites and determine best means to create rearing habitat | Population wide | 2d
Upper Trinity River | SONCC-UTR.2.2.63.2 | Floodplain and Channel Structure | Reconnect the channel to the floodplain | Construct off channel habitats, alcoves, backwater habitat, and old stream oxbows | Implement restoration projects that improve off channel habitats to create refugia habitat, as guided by assessment results | Population wide | 2d
Upper Trinity River | SONCC-UTR.2.2.64.1 | Floodplain and Channel Structure | Reconnect the channel to the floodplain | Increase beaver abundance | Develop a beaver conservation plan that includes education and outreach, technical assistance for land owners, and methods for reintroduction and/or relocation of beaver as a last resort | Population wide | 3d
Upper Trinity River | SONCC-UTR.2.2.64.1 | Floodplain and Channel Structure | Reconnect the channel to the floodplain | Increase beaver abundance | Reintroduce or relocate beaver if appropriate, guided by the plan | Population wide | 3d
Upper Trinity River | SONCC-UTR.2.2.64.2 | Floodplain and Channel Structure | Reconnect the channel to the floodplain | Increase beaver abundance | Implement education and technical assistance programs for landowners, guided by the plan | Population wide | 3d
Upper Trinity River | SONCC-UTR.2.2.7.1 | Floodplain and Channel Structure | Reconnect the channel to the floodplain | Construct off channel habitats, alcoves, backwater habitat, and old stream oxbows | Identify potential sites to create refugia habitats. Prioritize sites and determine best means to create rearing habitat | Mainstem, Grass Valley, Indian, Hayfork, Reading, Weaver, East Fork Weaver Creek, and all streams where coho salmon would benefit immediately | 2c
Upper Trinity River | SONCC-UTR.2.2.7.2 | Floodplain and Channel Structure | Reconnect the channel to the floodplain | Construct off channel habitats, alcoves, backwater habitat, and old stream oxbows | Implement restoration projects that improve off channel habitats to create refugia habitat, as guided by assessment results | Mainstem, Grass Valley, Indian, Hayfork, Reading, Weaver, East Fork Weaver Creek, and all streams where coho salmon would benefit immediately | 2c
Upper Trinity River | SONCC-UTR.2.2.8.1 | Floodplain and Channel Structure | Reconnect the channel to the floodplain | Increase beaver abundance | Reintroduce or relocate beaver if appropriate, guided by the plan | Grass Valley, Indian, Hayfork, Reading, Weaver, East Fork Weaver Creek, and all streams where coho salmon would benefit immediately | 3c
Upper Trinity River | SONCC-UTR.2.2.8.1 | Floodplain and Channel Structure | Reconnect the channel to the floodplain | Increase beaver abundance | Develop a beaver conservation plan that includes education and outreach, technical assistance for land owners, and methods for reintroduction and/or relocation of beaver as a last resort | Grass Valley, Indian, Hayfork, Reading, Weaver, East Fork Weaver Creek, and all streams where coho salmon would benefit immediately | 3c
Upper Trinity River | SONCC-UTR.2.2.8.2 | Floodplain and Channel Structure | Reconnect the channel to the floodplain | Increase beaver abundance | Implement education and technical assistance programs for landowners, guided by the plan | Grass Valley, Indian, Hayfork, Reading, Weaver, East Fork Weaver Creek, and all streams where coho salmon would benefit immediately | 3c
Upper Trinity River | SONCC-UTR.26.1.58.1 | Low Population Dynamics | Increase population abundance | Rescue and relocate stranded juveniles | Survey coho-bearing tributaries and relocate juveniles stranded in drying pools | Population wide | 2c
Upper Trinity River | SONCC-UTR.27.1.27.1 | Monitor | Track population abundance, spatial structure, productivity, or diversity | Estimate abundance | Determine annual abundance of adult coho salmon | Population wide | 3d
Upper Trinity River | SONCC-UTR.27.1.28.1 | Monitor | Track population abundance, spatial structure, productivity, or diversity | Track life history diversity | Describe annual variation in migration timing, age structure, habitat occupied, and behavior | Population wide | 3d
Upper Trinity River | SONCC-UTR.27.1.29.1 | Monitor | Track population abundance, spatial structure, productivity, or diversity | Track surrogate for genetic diversity | Describe annual ratio of naturally-produced fish to hatchery-produced fish spawned for hatchery production | Trinity River Hatchery | 3d
Upper Trinity River | SONCC-UTR.27.1.30.1 | Monitor | Track population abundance, spatial structure, productivity, or diversity | Track indicators related to the stress 'Fishing and Collecting' | Annually estimate the commercial and recreational fisheries bycatch and mortality rate for wild SONCC coho salmon | Population wide | 3d
Upper Trinity River | SONCC-UTR.27.1.31.1 | Monitor | Track population abundance, spatial structure, productivity, or diversity | Track indicators related to the stress 'Hatchery Management' | Annually determine the percent of hatchery origin spawners (PHOS), percent of natural origin spawners (PNOS), and the proportion of natural influence (PNI) | Population wide | 3d
Upper Trinity River | SONCC-UTR.27.1.40.1 | Monitor | Track population abundance, spatial structure, productivity, or diversity | Estimate juvenile spatial distribution | Conduct presence/absence surveys for juveniles | Population wide | 3d
Upper Trinity River | SONCC-UTR.27.1.42.1 | Monitor | Track population abundance, spatial structure, productivity, or diversity | Refine methods for setting population types and targets | Develop supplemental or alternate means to set population types and targets | Population wide | 3d
Upper Trinity River | SONCC-UTR.27.1.42.2 | Monitor | Track population abundance, spatial structure, productivity, or diversity | Refine methods for setting population types and targets | If appropriate, modify population types and targets using revised methodology | Population wide | 3d
Upper Trinity River | SONCC-UTR.27.1.48.1 | Monitor | Track population abundance, spatial structure, productivity, or diversity | Track indicators related to the threat 'Invasive Species' | Identify the status and trend of invasive species | Population wide | 3d
Upper Trinity River | SONCC-UTR.27.1.53.1 | Monitor | Track population abundance, spatial structure, productivity, or diversity | Develop survival estimates | Install and annually operate a life cycle monitoring (LCM) station | Site to be determined | 3d
Upper Trinity River | SONCC-UTR.27.2.32.1 | Monitor | Track habitat condition | Track habitat indicators related to spawning, rearing, and migration | Measure indicators for spawning and rearing habitat. Conduct a comprehensive survey | Population wide | 3d
Upper Trinity River | SONCC-UTR.27.2.32.2 | Monitor | Track habitat condition | Track habitat indicators related to spawning, rearing, and migration | Measure indicators for spawning and rearing habitat once every 10 years, sub-sampling using GRTS technique | Population wide | 3d
Upper Trinity River | SONCC-UTR.27.2.33.1 | Monitor | Track habitat condition | Track habitat indicators related to the stress 'Lack of Floodplain and Channel Structure' | Measure the indicators, pool depth, pool frequency, D50, and LWD | All IP habitat | 3d
Upper Trinity River | SONCC-UTR.27.2.34.1 | Monitor | Track habitat condition | Track habitat indicators related to the stress 'Impaired Hydrologic Function' | Continuously measure the hydrograph | All IP habitat | 3d
Upper Trinity River | SONCC-UTR.27.2.34.2 | Monitor | Track habitat condition | Track habitat indicators related to the stress 'Impaired Hydrologic Function' | Identify instream flow needs for coho salmon | All IP habitat | 3d
Upper Trinity River | SONCC-UTR.27.2.46.1 | Monitor | Track habitat condition | Track habitat indicators related to the stress 'Barriers' | Assess barriers limiting distribution of coho salmon | All IP habitat | 3d
Upper Trinity River | SONCC-UTR.27.2.54.1 | Monitor | Track habitat condition | Track ocean productivity | Compile and analyze data obtained from ocean net surveys, hatchery returns, satellites and buoy arrays in the ocean | Population wide | 3d
Upper Trinity River | SONCC-UTR.27.4.49.1 | Monitor | Track threat | Describe road threat | Describe the status and trends of road treatments and road density at least once every five years | Population wide | 3d
Upper Trinity River | SONCC-UTR.27.4.50.1 | Monitor | Track threat | Describe threat of road-stream crossing barriers | Describe any new road-stream crossing barriers and any changes to existing road-stream crossing barriers at least once every five years | Population wide | 3d
Upper Trinity River | SONCC-UTR.27.4.51.1 | Monitor | Track threat | Describe threat of hatcheries | Describe status of development and implementation of applicable HGMPs at least one every five years | Population wide | 3d
Upper Trinity River | SONCC-UTR.27.4.52.1 | Monitor | Track threat | Describe threat of invasive species | Describe status and trend of abundance and distribution of invasive species annually | Population wide | 3d
Upper Trinity River | SONCC-UTR.3.1.16.1 | Hydrology | Improve flow timing or volume | Manage flows | Assess how climate change and likely reduced snowpack might influence water availability | Population wide | 3c
Upper Trinity River | SONCC-UTR.3.1.16.3 | Hydrology | Improve flow timing or volume | Manage flows | Update Trinity River allocations, if needed, based on assessments of ROD flows | Population wide | 3c
Upper Trinity River | SONCC-UTR.3.1.17.1 | Hydrology | Improve flow timing or volume | Educate stakeholders | Develop an educational program about water conservation programs and instream leasing programs | Coldwater mainstem tributaries, Grass Valley, Indian, Reading, Weaver, East Fork Weaver Creek | 3c
Upper Trinity River | SONCC-UTR.3.1.18.1 | Hydrology | Improve flow timing or volume | Improve regulatory mechanisms | Work with partners to streamline the process needed for the dedication or leasing of water to fish and wildlife resources under CA Water Code section 1707 | Population wide | 2b
Upper Trinity River | SONCC-UTR.3.1.18.2 | Hydrology | Improve flow timing or volume | Improve regulatory mechanisms | Implement water dedications and leases to increase instream flows using the streamlined process | Population wide | 2b
Upper Trinity River | SONCC-UTR.3.1.20.1 | Hydrology | Improve flow timing or volume | Improve regulatory mechanisms | Establish a comprehensive groundwater permit process | Population wide | 2b
Upper Trinity River | SONCC-UTR.3.1.21.1 | Hydrology | Improve flow timing or volume | Increase instream flows | Assess basin wide water diversion projects and prioritize areas in need of increased flows. Develop a plan to obtain adequate flows for riparian resources | Population wide | 2c
Upper Trinity River | SONCC-UTR.3.1.21.2 | Hydrology | Improve flow timing or volume | Increase instream flows | Reduce diversions, guided by the plan | Population wide | 2c
Upper Trinity River | SONCC-UTR.3.1.36.1 | Hydrology | Improve flow timing or volume | Increase instream flows | Establish a forbearance program, using water storage tanks to decrease diversion during periods of low flow | Mainstem above Douglas City, Grass Valley, Indian, Hayfork, Reading, Weaver, East Fork Weaver creeks, and all streams where coho salmon would benefit immediately | 2c
Upper Trinity River | SONCC-UTR.3.1.36.2 | Hydrology | Improve flow timing or volume | Increase instream flows | Monitor forbearance compliance and flow | Mainstem above Douglas City, Grass Valley, Indian, Hayfork, Reading, Weaver, East Fork Weaver creeks, and all streams where coho salmon would benefit immediately | 2c
Upper Trinity River | SONCC-UTR.3.1.37.1 | Hydrology | Improve flow timing or volume | Increase instream flows | Pump water from mainstem Trinity River for Weaverville municipal water supply during periods of low flow | Weaver and East Weaver creeks | 2c
Upper Trinity River | SONCC-UTR.3.1.38.1 | Hydrology | Improve flow timing or volume | Improve water management techniques | Develop a plan to manage stream flows and water temperature during periods of drought, protecting coho salmon from effects of climate change | All streams where coho salmon would benefit immediately | 3c
Upper Trinity River | SONCC-UTR.3.1.38.2 | Hydrology | Improve flow timing or volume | Improve water management techniques | Implement plan based on findings | All streams where coho salmon would benefit immediately | 3c
Upper Trinity River | SONCC-UTR.3.1.44.1 | Hydrology | Improve flow timing or volume | Secure and maintain sufficient instream flows | Identify and cease unauthorized water diversions | North Fork Trinity River and Canyon, Browns, Reading, Weaver, Middle Weaver Creeks, Grass Valley, Indian, Hayfork, Reading, Weaver, East Fork Weaver Creek, and all streams where coho salmon would benefit immediately | 2c
Upper Trinity River | SONCC-UTR.3.1.45.1 | Hydrology | Improve flow timing or volume | Determine effects of marijuana cultivation | Assess cumulative effects (e.g., flow, water quality) of marijuana cultivation | Population wide | 3c
Upper Trinity River | SONCC-UTR.3.1.45.2 | Hydrology | Improve flow timing or volume | Determine effects of marijuana cultivation | If needed, develop plan to reduce effects of marijuana cultivation | Population wide | 3c
Upper Trinity River | SONCC-UTR.3.1.45.3 | Hydrology | Improve flow timing or volume | Determine effects of marijuana cultivation | Implement plan | Population wide | 3c
Upper Trinity River | SONCC-UTR.3.1.59.1 | Hydrology | Improve flow timing or volume | Provide adequate instream flow for coho salmon | Conduct study to determine instream flow needs of coho salmon at all life stages. | Population wide | 2c
Upper Trinity River | SONCC-UTR.3.1.59.2 | Hydrology | Improve flow timing or volume | Provide adequate instream flow for coho salmon | If coho salmon instream flow needs are not being met, develop plan to provide adequate flows. Plan may include water conservation incentives for landowners and re-assessment of water allocation. | Population wide | 2c
Upper Trinity River | SONCC-UTR.3.1.59.3 | Hydrology | Improve flow timing or volume | Provide adequate instream flow for coho salmon | Implement coho salmon instream flow needs plan. | Population wide | 2c
Upper Trinity River | SONCC-UTR.3.1.65.1 | Hydrology | Improve flow timing or volume | Increase instream flows | Establish a forbearance program, using water storage tanks to decrease diversion during periods of low flow | Population wide | 2d
Upper Trinity River | SONCC-UTR.3.1.65.2 | Hydrology | Improve flow timing or volume | Increase instream flows | Monitor forbearance compliance and flow | Population wide | 2d
Upper Trinity River | SONCC-UTR.3.1.66.1 | Hydrology | Improve flow timing or volume | Improve water management techniques | Develop a plan to manage stream flows and water temperature during periods of drought, protecting coho salmon from effects of climate change | Population wide | 3d
Upper Trinity River | SONCC-UTR.3.1.66.2 | Hydrology | Improve flow timing or volume | Improve water management techniques | Implement plan based on findings | Population wide | 3d
Upper Trinity River | SONCC-UTR.3.1.67.1 | Hydrology | Improve flow timing or volume | Secure and maintain sufficient instream flows | Identify and cease unauthorized water diversions | Population wide | 2d
Upper Trinity River | SONCC-UTR.5.1.10.1 | Passage | Improve access | Remove barriers | Assess highest priority road-stream and diversion related barriers. Develop a plan for removal | North Fork Trinity and Canyon, Browns, Reading, Weaver, Middle Weaver Creeks, and all streams where coho salmon would benefit immediately | 3c
Upper Trinity River | SONCC-UTR.5.1.10.2 | Passage | Improve access | Remove barriers | Remove barriers, guided by the plan | North Fork Trinity and Canyon, Browns, Reading, Weaver, Middle Weaver Creeks, and all streams where coho salmon would benefit immediately | 3c
Upper Trinity River | SONCC-UTR.5.1.11.1 | Passage | Improve access | Reduce sediment barriers | Inventory and prioritize barriers formed by alluvial deposits | Tributary confluences where coho salmon would benefit immediately | 3c
Upper Trinity River | SONCC-UTR.5.1.11.2 | Passage | Improve access | Reduce sediment barriers | Remove alluvial deposits, construct low flow channels, or reduce stream gradient to provide fish passage at all life stages | Tributary confluences where coho salmon would benefit immediately | 3c
Upper Trinity River | SONCC-UTR.5.1.35.1 | Passage | Improve access | Provide artificial passage | Study feasibility of fish passage at Lewiston and Trinity dams | Lewiston and Trinity Dams | 2c
Upper Trinity River | SONCC-UTR.5.1.35.2 | Passage | Improve access | Provide artificial passage | Provide passage for all life stages, guided by plan | Lewiston and Trinity Dams | 2c
Upper Trinity River | SONCC-UTR.5.1.68.1 | Passage | Improve access | Remove barriers | Assess highest priority road-stream and diversion related barriers. Develop a plan for removal | Population wide | 3d
Upper Trinity River | SONCC-UTR.5.1.68.2 | Passage | Improve access | Remove barriers | Remove barriers, guided by the plan | Population wide | 3d
Upper Trinity River | SONCC-UTR.5.1.69.1 | Passage | Improve access | Reduce sediment barriers | Inventory and prioritize barriers formed by alluvial deposits | Population wide | 3d
Upper Trinity River | SONCC-UTR.5.1.69.2 | Passage | Improve access | Reduce sediment barriers | Remove alluvial deposits, construct low flow channels, or reduce stream gradient to provide fish passage at all life stages | Population wide | 3d
Wilson Creek | SONCC-WilC.10.7.23.1 | Water Quality | Restore nutrients | Add marine-derived nutrients to streams | Develop a plan to supply appropriate amounts of marine-derived nutrients to streams (e.g. carcass placement, pellet dispersal) | All streams where coho salmon would benefit immediately | 3c
Wilson Creek | SONCC-WilC.10.7.23.2 | Water Quality | Restore nutrients | Add marine-derived nutrients to streams | Supply marine-derived nutrients to streams guided by the plan | All streams where coho salmon would benefit immediately | 3c
Wilson Creek | SONCC-WilC.10.7.25.1 | Water Quality | Restore nutrients | Add marine-derived nutrients to streams | Develop a plan to supply appropriate amounts of marine-derived nutrients to streams (e.g. carcass placement, pellet dispersal) | Population wide | 3d
Wilson Creek | SONCC-WilC.10.7.25.2 | Water Quality | Restore nutrients | Add marine-derived nutrients to streams | Supply marine-derived nutrients to streams guided by the plan | Population wide | 3d
Wilson Creek | SONCC-WilC.2.1.1.1 | Floodplain and Channel Structure | Increase channel complexity | Increase LWD, boulders, or other instream structure | Assess habitat to determine beneficial location and amount of instream structure needed | Unnamed creeks south of Crescent City and Wilson Creek, and all streams where coho salmon would benefit immediately | 2b
Wilson Creek | SONCC-WilC.2.1.1.2 | Floodplain and Channel Structure | Increase channel complexity | Increase LWD, boulders, or other instream structure | Place instream structures, guided by assessment results | Unnamed creeks south of Crescent City and Wilson Creek, and all streams where coho salmon would benefit immediately | 2b
Wilson Creek | SONCC-WilC.2.1.24.1 | Floodplain and Channel Structure | Increase channel complexity | Determine restoration potential in streams other than Wilson Creek | Conduct presence/absence surveys and habitat inventory to determine restoration potential for coho salmon. Develop a plan for restoration if warranted. | All streams in population area excluding Wilson Creek | 3d
Wilson Creek | SONCC-WilC.2.1.24.2 | Floodplain and Channel Structure | Increase channel complexity | Determine restoration potential in streams other than Wilson Creek | Restore streams, guided by the plan | All streams in population area excluding Wilson Creek | 3d
Wilson Creek | SONCC-WilC.2.1.26.1 | Floodplain and Channel Structure | Increase channel complexity | Increase LWD, boulders, or other instream structure | Assess habitat to determine beneficial location and amount of instream structure needed | Population wide | 2c
Wilson Creek | SONCC-WilC.2.1.26.2 | Floodplain and Channel Structure | Increase channel complexity | Increase LWD, boulders, or other instream structure | Place instream structures, guided by assessment results | Population wide | 2c
Wilson Creek | SONCC-WilC.2.2.10.1 | Floodplain and Channel Structure | Reconnect the channel to the floodplain | Increase beaver abundance | Develop a beaver conservation plan that includes education and outreach, technical assistance for land owners, and methods for reintroduction and/or relocation of beaver as a last resort | Unnamed creeks south of Crescent City, Lower Wilson Creek, and all streams where coho salmon would benefit immediately | 2b
Wilson Creek | SONCC-WilC.2.2.10.2 | Floodplain and Channel Structure | Reconnect the channel to the floodplain | Increase beaver abundance | Implement education and technical assistance programs for landowners, guided by the plan | Unnamed creeks south of Crescent City, Lower Wilson Creek, and all streams where coho salmon would benefit immediately | 2b
Wilson Creek | SONCC-WilC.2.2.10.3 | Floodplain and Channel Structure | Reconnect the channel to the floodplain | Increase beaver abundance | Reintroduce or relocate beaver if appropriate, guided by the plan | Unnamed creeks south of Crescent City, Lower Wilson Creek, and all streams where coho salmon would benefit immediately | 2b
Wilson Creek | SONCC-WilC.2.2.11.1 | Floodplain and Channel Structure | Reconnect the channel to the floodplain | Construct off channel habitats, alcoves, backwater habitat, and old stream oxbows | Identify potential sites to create refugia habitats. Prioritize sites and determine best means to create rearing habitat | Unnamed creeks south of Crescent City and Lower Wilson Creek, and all streams where coho salmon would benefit immediately | 2b
Wilson Creek | SONCC-WilC.2.2.11.2 | Floodplain and Channel Structure | Reconnect the channel to the floodplain | Construct off channel habitats, alcoves, backwater habitat, and old stream oxbows | Implement restoration projects that improve off channel habitats to create refugia habitat, as guided by assessment results | Unnamed creeks south of Crescent City and Lower Wilson Creek, and all streams where coho salmon would benefit immediately | 2b
Wilson Creek | SONCC-WilC.2.2.21.1 | Floodplain and Channel Structure | Reconnect the channel to the floodplain | Improve regulatory mechanisms | Improve protective regulations for beaver and develop guidelines for relocation that are practical for restoration groups | Population wide | 2c
Wilson Creek | SONCC-WilC.2.2.27.1 | Floodplain and Channel Structure | Reconnect the channel to the floodplain | Increase beaver abundance | Develop a beaver conservation plan that includes education and outreach, technical assistance for land owners, and methods for reintroduction and/or relocation of beaver as a last resort | Population wide | 2c
Wilson Creek | SONCC-WilC.2.2.27.2 | Floodplain and Channel Structure | Reconnect the channel to the floodplain | Increase beaver abundance | Implement education and technical assistance programs for landowners, guided by the plan | Population wide | 2c
Wilson Creek | SONCC-WilC.2.2.27.3 | Floodplain and Channel Structure | Reconnect the channel to the floodplain | Increase beaver abundance | Reintroduce or relocate beaver if appropriate, guided by the plan | Population wide | 2c
Wilson Creek | SONCC-WilC.2.2.28.1 | Floodplain and Channel Structure | Reconnect the channel to the floodplain | Construct off channel habitats, alcoves, backwater habitat, and old stream oxbows | Identify potential sites to create refugia habitats. Prioritize sites and determine best means to create rearing habitat | Population wide | 2c
Wilson Creek | SONCC-WilC.2.2.28.2 | Floodplain and Channel Structure | Reconnect the channel to the floodplain | Construct off channel habitats, alcoves, backwater habitat, and old stream oxbows | Implement restoration projects that improve off channel habitats to create refugia habitat, as guided by assessment results | Population wide | 2c
Wilson Creek | SONCC-WilC.27.1.12.1 | Monitor | Track population abundance, spatial structure, productivity, or diversity | Estimate juvenile spatial distribution | Conduct presence/absence surveys for juveniles | Population wide | 3d
Wilson Creek | SONCC-WilC.27.1.13.1 | Monitor | Track population abundance, spatial structure, productivity, or diversity | Refine methods for setting population types and targets | Develop supplemental or alternate means to set population types and targets | Population wide | 3d
Wilson Creek | SONCC-WilC.27.1.13.2 | Monitor | Track population abundance, spatial structure, productivity, or diversity | Refine methods for setting population types and targets | If appropriate, modify population types and targets using revised methodology | Population wide | 3d
Wilson Creek | SONCC-WilC.27.1.20.1 | Monitor | Track population abundance, spatial structure, productivity, or diversity | Track indicators related to the stress 'Fishing and Collecting' | Annually estimate the commercial and recreational fisheries bycatch and mortality rate for wild SONCC coho salmon | Population wide | 3d
Wilson Creek | SONCC-WilC.27.1.9.1 | Monitor | Track population abundance, spatial structure, productivity, or diversity | Assess coho habitat use | Assess coho population use of tributaries and other small streams on RNSP lands | Unnamed creeks south of Crescent City | 3d
Wilson Creek | SONCC-WilC.27.1.9.2 | Monitor | Track population abundance, spatial structure, productivity, or diversity | Assess coho habitat use | Assess coho population use of tributaries and other small streams on private lands | Unnamed creeks south of Crescent City | 3d
Wilson Creek | SONCC-WilC.27.2.15.1 | Monitor | Track habitat condition | Track habitat indicators related to the stress 'Lack of Floodplain and Channel Structure' | Measure the indicators, pool depth, pool frequency, D50, and LWD | All IP habitat | 3d
Wilson Creek | SONCC-WilC.27.2.16.1 | Monitor | Track habitat condition | Track habitat indicators related to the stress 'Degraded Riparian Forest Condition' | Measure the indicators, canopy cover, canopy type, and riparian condition | All IP habitat | 3d
Wilson Creek | SONCC-WilC.27.2.17.1 | Monitor | Track habitat condition | Track habitat indicators related to the stress 'Altered Sediment Supply' | Measure the indicators, % sand, % fines, V Star, silt/sand surface, turbidity, embeddedness | All IP habitat | 3d
Wilson Creek | SONCC-WilC.27.2.22.1 | Monitor | Track habitat condition | Track ocean productivity | Compile and analyze data obtained from ocean net surveys, hatchery returns, satellites and buoy arrays in the ocean | Population wide | 3d
Wilson Creek | SONCC-WilC.27.2.8.1 | Monitor | Track habitat condition | Track habitat indicators related to spawning, rearing, and migration | Measure indicators for spawning and rearing habitat. Conduct a comprehensive survey | Population wide | 3d
Wilson Creek | SONCC-WilC.27.2.8.2 | Monitor | Track habitat condition | Track habitat indicators related to spawning, rearing, and migration | Measure indicators for spawning and rearing habitat once every 15 years, sub-sampling using GRTS technique | Population wide | 3d
Wilson Creek | SONCC-WilC.27.4.18.1 | Monitor | Track threat | Describe road threat | Describe the status and trends of road treatments and road density at least once every five years | Population wide | 3d
Wilson Creek | SONCC-WilC.27.4.19.1 | Monitor | Track threat | Describe mining/gravel extraction threat | Describe any new mining or gravel extraction and any changes to existing mining and gravel extraction at least once every five years | Population wide | 3d
Wilson Creek | SONCC-WilC.5.1.29.1 | Passage | Improve access | Remove structural barriers | Assess barriers and prioritize for removal or upgrade to ensure passage at all life-stages | Population wide | 2c
Wilson Creek | SONCC-WilC.5.1.29.2 | Passage | Improve access | Remove structural barriers | Remove barriers, based on evaluation | Population wide | 2c
Wilson Creek | SONCC-WilC.5.1.4.1 | Passage | Improve access | Remove barriers | Evaluate and prioritize barriers for removal | Lagoon Creek and unnamed coastal creeks, Highway 101 | 2b
Wilson Creek | SONCC-WilC.5.1.4.2 | Passage | Improve access | Remove barriers | Remove barriers, based on evaluation | Lagoon Creek and unnamed coastal creeks, Highway 101 | 2b
Wilson Creek | SONCC-WilC.5.1.5.1 | Passage | Improve access | Remove structural barriers | Assess barriers and prioritize for removal or upgrade to ensure passage at all life-stages | All streams where coho salmon would benefit immediately | 2b
Wilson Creek | SONCC-WilC.5.1.5.2 | Passage | Improve access | Remove structural barriers | Remove barriers, based on evaluation | All streams where coho salmon would benefit immediately | 2b
Wilson Creek | SONCC-WilC.7.1.2.1 | Riparian | Improve wood recruitment, bank stability, shading, and food subsidies | Increase conifer riparian vegetation | Develop an appropriate timber harvest management plan for benefits to coho salmon habitat | Population wide | 2c
Wilson Creek | SONCC-WilC.7.1.2.2 | Riparian | Improve wood recruitment, bank stability, shading, and food subsidies | Increase conifer riparian vegetation | Thin, or release conifers, guided by the plan | Population wide | 2c
Wilson Creek | SONCC-WilC.7.1.2.3 | Riparian | Improve wood recruitment, bank stability, shading, and food subsidies | Increase conifer riparian vegetation | Plant conifers, guided by the plan | Population wide | 2c
Wilson Creek | SONCC-WilC.7.1.3.1 | Riparian | Improve wood recruitment, bank stability, shading, and food subsidies | Improve timber harvest practices | Apply best management practices for timber harvest | Population wide | 3d
Wilson Creek | SONCC-WilC.8.1.30.1 | Sediment | Reduce delivery of sediment to streams | Reduce road-stream hydrologic connection | Decommission roads, guided by Wilson Creek Watershed Assessment and Erosion Prevention Planning Project | Population wide | 2d
Wilson Creek | SONCC-WilC.8.1.7.1 | Sediment | Reduce delivery of sediment to streams | Reduce road-stream hydrologic connection | Decommission roads, guided by Wilson Creek Watershed Assessment and Erosion Prevention Planning Project | RNSP lands in lower Wilson Creek, Nickel Creek, and unnamed tributaries; and all streams where coho salmon would benefit immediately | 2c